## summary
goal | milestone | priority | lead
Collect | Collect and index forge metadata | 1 – High | vlorentz
Collect | Tooling for takedown notices | 1 – High | lunar | 50%
Preserve | Explore possibility of replacing SHA1 with SHA1-DC | 1 – High | olasd | 100%
Preserve | Publicly available standard for SWHID version 1 | 1 – High | rdicosmo | 100%
Preserve | SWH Mirror at ENEA | 1 – High | douardda | 100%
Preserve | Mirrors tooling | 1 – High | douardda | 66%
Preserve | Support archiving repositories containing SHA1 hash conflicts on blobs | 1 – High | olasd | 0%
Share | Release a first version of the swh-scanner product | 1 – High | bchauvet | 30%
Share | Webhook-based notification for long-running user tasks | 1 – High | anlambert
Share | Self-host Software Stories software stack | 1 – High | bchauvet | 20%
Share | Design presentation of Metadata on Web UI | 1 – High | moranegg
Documentation | Provide a landing page for docs.s.o | 1 – High | Lunar | 100%
Technical debt | Setup efficient and consistent swh-storage pagination | 1 – High | jayesh
Technical debt | Improve support for malformed git commits | 1 – High | vlorentz
Tooling and infrastructure | Dynamic infrastructure | 1 – High | vsellier
Tooling and infrastructure | Provide a management-friendly monitoring dashboard of services | 1 – High | vsellier
Tooling and infrastructure | Provenance in production | 1 – High | douardda
Tooling and infrastructure | Scale-out objstorage in production as primary objstorage | 1 – High | olasd
Tooling and infrastructure | Cassandra in production as primary storage | 1 – High | vsellier
Tooling and infrastructure | Graph export and graph compression in production | 1 – High | vlorentz
Collect | Minimize archival lag w.r.t. upstream code hosting platforms | 2 – Medium | olasd
Collect | Extend archive coverage | 2 – Medium | ardumont
Preserve | Regularly scrub journal storage and objstorage | 2 – Medium | vlorentz
Preserve | SWH Mirror at GRNET | 2 – Medium | douardda
Preserve | Archive cold-copy at CINES via Vitam | 2 – Medium | douardda | 0%
Share | Propose Web UI sections for dedicated partner collections | 2 – Medium | bchauvet | 0%
Share | Create a cost-calculator in the Vault | 2 – Medium | vlorentz
Share | Publish derived datasets | 2 – Medium | vlorentz | 100%
Share | Evaluate the storage of indexed metadata in a triple-store | 2 – Medium | vlorentz
Tooling and infrastructure | Use a common workflow management tool for swh-web | 2 – Medium | lunar
Tooling and infrastructure | Design and test a Continuous Deployment infrastructure | 2 – Medium | vsellier
Collect | Add support for write APIs features in GraphQL | 3 – Low | jayesh
Collect | Automate add forge now | 3 – Low | vsellier
Preserve | SWH Mirror at Duisburg-Essen university | 3 – Low | douardda | 0%
Tooling and infrastructure | Design and test next generation CI Automation | 3 – Low | olasd